Start:			Finalize:

  - October 20XX  	December 20XX (Completed)

    - December 20XX 		May 20XX

    - May 20XX	January 20XX

    - January 20XX	November 20XX

    - November 20XX

I	January 20XX

Total Time: 26 Months

Process for forming the RFA work plan

- RFA Steering Committee (RFASC) established
Fire Chiefs recommend five members from their jurisdiction

  - RFAPC approves the make-up of the RFASC

  - Chair and Vice-Chair for the RFASC are elected by RFASC members

  - RFAPC approves the Chair and Vice-Chair

  - Secretary for the RFASC is appointed by RFASC Chair

  - RFAPC approves the appointment of the Secretary

  - RFASC rules, process and purpose are established by RFASC

  - RFAPC approves the RFASC rules

  - RFASC Meeting Times and dates are set by the RFASC

- Vision Development

  - RFAPC provides the RFASC with elements of their vision

  - RFASC establishes a consensus draft vision statement

  - RFAPC formally adopts the vision statement and considers joint resolution

- Communications Plan Developed

  - RFASC develops internal and external communications plan

  - RFAPC approves internal and external communications plan

  - RFASC implements internal and external communications plan

- Financial Plan for Work Plan Development

  - RFASC develops financial plan

  - RFAPC approves financial plan

  - RFASC manages financial plan

- Project Task List process established

- RFASC develops project task list for work plan

- RFAPC approves project task list for work plan

- RFASC establishes strategic statement for each category

- RFAPC approves strategic statement for each category

- RFASC establishes sub-committee and lead for each Project Task

- RFAPC approves sub-committee and lead for each Project Task

- RFASC establishes timelines for each Project Task sub-committee

- RFAPC approves timelines for each Project Task sub-committee

- Work plan finalized

  - RFASC compiles comprehensive report on RFA Work Plan

  - RFAPC considers approval of comprehensive report on RFA Work Plan

  - RFAPC considers joint resolution to approve RFA work plan by all elected boards

- Election Plan Developed

  - RFASC develops comprehensive election information plan

  - RFAPC considers approval of comprehensive election information plan

  - RFASC implements approved election information plan

- Election Held

- [RFA Name] Plan Implemented

Approved Project Tasks Items (Per E2 above)

- Name of the New Organization

- Governing Board

- Revenue and Expenses

- Legal Considerations

- ORG Chart

  - Operations

  - Admin

  - Fire Prevention

  - Training

  - EMS

  - Clerical support

  - Facilities, Vehicles and Supply

  - Financial

  - Human Resources

  - Planning/Accreditation

- Volunteer Members

- Collective Bargaining Agreements

- Standard of Response Coverage

  - Strategic staffing plan

  - Strategic facilities plan

  - Strategic services plan

- Future Expansion of the RFA

- Information/ Election Strategy